## Project Pursuit summary
Background / opportunity source
Project Name | *** this name should be matched to other sheets
Scope to be completed
Project expected deliverables from client
Proposal timeline (due date to submit)
Project timeline (start and end dates)
Project Stakeholders
Project Bid requirements
Identified potential Risk items
Info supplied by client
Communications notes
Opportunity for additional value
SR&ED Opportunity

## project complexity evaluation
Project Evaluation
Reference #: |  |  | Project Name:
Pursuit Lead |  |  | Project Sponsor/Client:
Date:
COMPLEXITY RATING
EVALUATION DIMENSION | DESCRIPTION | 1 | 2 | 3 | 4
CLIENT | Client management | Experienced | - | Inexperienced | Difficult
| Profile of project | None | Local | Regional | National profile
SCOPE | Clarity of scope | Clearly defined, no ambiguity | Defined, limited ambiguity | Need to be clarified and developed | Only outcomes identified
| Requirement for professional services sub-consultant | None | Same location, or low % of fees | National, or <25% of fees | International, or >25% of fees
FINANCE & CONTRACT | Total Compensation, or annual average if same scope over multiple years | Up to $25k | $25k to $100k | $100k to $1m | Greater than $1m
EXECXUTION METHODOLOGY | Scope management | Well documented | Minor development | Substantial development | Requires new or novel approach
COMMS | Number of disciplines, includes external suppliers | One | Two | Three to five | More than five
| Number of Staff involved, includes external suppliers | Less than 5 | 5-10 | 10-50 | Greater than 50
SCHEDULE | Schedule Speed | Relaxed | Some float | No float but manageable | Pressured
| Project Duration | Less than a week | upto a month | upto 1 year | 1-5 years
HEALTH & SAFETY | Where is the work going to be completed | Job Hazard Assesment Health & Safety controls will be sufficient for the project | All team members can easily meet face to face | PM has difficulty meeting entire team face to face in one place | Geographically Dispersed Team
FIRST NATIONS AWARENESS | Extent of interaction | None | Contract requires methodology for participation | First Nations employment requirement, interaction with leaders & businesses | Complex interactions, multiple layers of government, businesses and bands
POTENTIAL FOR INNOVATION AND SRE&ED |  | YES |  | NO
| Evaluated Complexity Rating | 1 | 2 | 3 | 4
| Project Manager would need to have additional skills in: (SELECT ALL RELEVANT) | Finance or contract | Communications | Client Awareness | Innovation and Creativity
Assessment carried out by: |  | Scope Management | Time Management | Health and Safety | Other
NAME |  | ROLE |  | SIGNATURE | DATE
****Use the following instructions for formatting the table above and use create a user interface for this process
PROJECT COMPLEXITY / RISK
DIMENSION | DESCRIPTION | 1 | 2 | 3 | 4
FINANCE & CONTRACT | Total Compensation, or annual average if same scope over multiple years | 1 | 2 | 3 | 4 | assign values to these boxes and allow a user to click and save and click on one value for each row
COMMS | Number of disciplines, includes external suppliers | 1 | 2 | 3 | 4
| Number of Staff involved, includes external suppliers | 1 | 2 | 3 | 4
SCOPE | Clarity of scope | 1 | 2 | 3 | 4
| Requirement for professional services sub-consultant | 1 | 2 | 3 | 4
SCHEDULE | Schedule Speed | 1 | 2 | 3 | 4
| Project Duration | 1 | 2 | 3 | 4
CLIENT | Client management | 1 | 2 | 3 | 4
| Profile of project | 1 | 2 | 3 | 4
EXECXUTION METHODOLOGY | Scope management | 1 | 2 | 3 | 4
HEALTH & SAFETY | Where is the work going to be completed | 1 | 2 | 3 | 4
FIRST NATIONS AWARENESS | Extent of interaction | 1 | 2 | 3 | 4
POTENTIAL FOR INNOVATION AND SRE&ED |  | 2 |  | 4
| range | 1 to 12 | 13 to 24 | 25 to 33 | 34 to 48
| Project Manager level | 1 | 2 | 3 | 4

## go-noGo
OPPORTUNITY Evaluation GO/NO GO Assesment
Reference #: |  | Project Name:
Pursuit Lead |  | Project Sponsor/Client:
Date:
| 8 7 6 | 5 4 3 | 2 1 0 | Rating (0-8)
CLIENT |  |  |  |  | ***assign values to rating boxes in this column and highlight corresponding columns by allowing user to entering a value in the ratings column the total will reflect the ranges noted below create a user interface which will match this presentation ***the colours shown indicate an example of sample formatting, feel free to create UI which is more subtle
Do we have an established relationship with client | Good; we work with them often and meet regularly | Average - Fair; we have done some work with them or met them occasionally | Poor; we don't really know them ad have not had much or any contact | 8
Is this a Client relationship we really want to develop? | Most certainly | Yes, we think so | Umm, not really too sure about that | 8
Have there been any issues regarding payment when invoicing this client? | No | sometimes | all the time | 8
PROJECT
What is the amount of scope required to be completed in the Project | large | moderate | limited | 2
how high are margins/Profitability expected for this project | High | Moderate | Low | 5
Do we have the skills, experience and capability and competence to execute the defined scope of work | Good | Fair | Poor | 8
Do we have Track record (performance on relevant projects) | Good | Fair | Poor | 8
Do we have the human and equipment resources to complete the project requirements | Well Qualified | Qualified | Minimal/None | 8
Any issues with the contract? Liability, indemnity, insurance? | No, terms are pretty standard | Some issues, but we should be able to overcome them | Yes, some significant issues we will struggle to deal with | 8
Business Intelligence Info on client | Good; we know exactly what the client is looking for | Fair; we have some idea of where they are coming from and what they want | Poor; no idea really, we are just responding to a request to tender | 5
Adequacy of information to bid e.g. brief | Clear | Some unclear elements | Unclear | 5
Resource availability to prepare proposal, incl. Pursuit lead | Good | Adequate | Inadequate | 6
Level of competition – strength and number; can we win? | Weak - we are easily the front-runner and should be able to win | Moderate - some good competitors, but none we can't beat | Strong - lots of competitors and in far better positions than us to win | 8
Probability of success | >50% | 30-50% | <30% | 8
Corporate alignment
Alignment with Company Vision and adopted Strategy | High - exactly where we want to be | Moderate - some fit, some not | Little/None | 5
Potential to generate positive profile | Good | Fair | Little/None | 8
Project Risks | Yes, risk assessment complete, we know what we're in for | Somewhat - we can see some of the risks but unsure how to manage some of them | Not really - no assessment done. We are in an unfamiliar territory/market | 5
Ability to establish a long term relationship with client, or establish ourselves in market | Good | Fair | Little/None | 8
|  |  | OVERALL RATING | 121
SUMMARY From Business Intelligence Info
NOTES / COMMENTS:
| This Form's Indication: |  | The Decision
| GO indicators are normally based on an overall rating of 108 or greater |  | GO | NO GO
Ratings between 55 & 109 should be discussed with a Project Directors
Overall rating of less than 54, normally indicate a NO GO
Project Complexity Assessment
dd-mm-yyyy
dd-mm-yyyy
Approved by
Prepared by
Date
Date

## schedule of hourly rates
Position | Comments | Rate | Unit
Project Director/ Professional Land Surveyors, Professional Engineers | Professional Services and Advisory |  | hour
Project Manager | Project direction, budgeting, scheduling, cost tracking and reporting |  | hour
Project Coordinator | Coordination of Project tasks, quality control, calculations, tracking and reporting |  | hour
Geomatics Technician | Quality Control/Quality Assurance of field surveyed data, CAD Drafting, Computations and Post Processing. Includes computers, software, plotters, copiers. |  | hour
Documentation Technician | Document Control. Preparation and registration of plans and documents |  | hour
Survey Crew (One Person) | Includes electronic field equipment - laptop, pipe locator, radio/telephone, pin finder, digital camera, vehicle (4x4), GPS Equipment. |  | hour
Survey Crew (Two Person) | Includes electronic field equipment - laptop, pipe locator, radio/telephone, pin finder, digital camera, vehicle (4x4), GPS Equipment. |  | hour
Survey Crew (Three Person) | Includes electronic field equipment - laptop, pipe locator, radio/telephone, pin finder, digital camera, vehicle (4x4), GPS Equipment. |  | hour
Additional crew member |  |  | hour
Safety Coordinator | Includes cell phone, camera, safety gear |  | hour
Administration | Cost Control, Invoicing, Information Search |  | hour
Equipment | Comments | Rate | Unit
Vehicle (4 x 4) | Whichever the greater for any day. |  | hour
km
All Terrain Vehicle | Quad or snowmobile. |  | day
UAV/Drone | Field equipment |  | day
GPS Equipment |  |  | day
Total Station |  |  | day
Line locating equipment (Pipe and Cable Locator) |  |  | day
Terrestrial Laser Scanner |  |  | day
Hydrographic Survey Package | Includes boat, Depth Sounder, Processing Software |  | day
Supplies & Disbursements | Comments | Rate | Unit
Field & Office supplies including disbursements | Includes equipment rentals, deliveries, Lath, Flagging, Paint, Office Supplies, Land Titles Registration Fees, Fuel, etc. Minimum $100 per project |  | day
Subsistence | Meals Only |  | /2person per day
| Lodging |  | /2person per day
| Or Minimum |  | /2person per day
Mob/demob crew rate |  |  | /mob/demob

## work breakdown structure
project stages | Scope and Description of work | Professional Land Surveyors, Professional Engineers | Project Manager | Project Coordinator | Geomatics Technician | Documentation Technician | 1 person survey crew | 2 person survey crew | 3 person survey crew | Additional crew member | Safety Coordinator | Administration | Vehicle usage mileage(km) | Vehicle usage hours | All Terrain Vehicle | UAV/Drone | GPS Equipment | Total Station | Line locating equipment (Pipe and Cable Locator) | Terrestrial Laser Scanner | Hydrographic Survey Package | legal survey title, parcel mapping and right of way plans | Accommodation | Subsistence | Mobilization/Demobilization
Pursuit and Work Breakdown Structure
Initiating& Planning
Field Execution Scope of work
Data Analysis, Processing & Deliverables
Close out
Totals (hr) = |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0%
0%

## budgetary estimate
[7 empty] | cost of labour |  | total labour cost
LABOR
Professional Land Surveyors, Professional Engineers | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Project Manager | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Project Coordinator | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Geomatics Technician | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Documentation Technician | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Survey Crew (One Person) | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Survey Crew (Two Person) | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Survey Crew (Three Person) | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Additional Man | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Safety Coordinator | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
Administration | 0 | hrs@ | 0 | /hr | 0 |  | 0 |  | 0
[5 empty] | 0 | average rate labour cost | 0 | total labour cost | 0
EQUIPMENT
Vehicle (4 x 4) | 0 | km@ | 0 | /km | 0 |  | 0
Vehicle (4 x 4) | 0 | hrs@ | 0 | /hr | 0 |  | 0
All Terrain Vehicle | 0 | days@ | 0 | /day | 0 |  | 0
UAV/Drone | 0 | days@ | 0 | /day | 0 |  | 0
GPS Equipment | 0 | days@ | 0 | /day | 0 |  | 0
Total Station | 0 | days@ | 0 | /day | 0 |  | 0
Line locating equipment (Pipe and Cable Locator) | 0 | days@ | 0 | /day | 0 |  | 0
Terrestrial Laser Scanner | 0 | days@ | 0 | /day | 0 |  | 0
Hydrographic Survey Package | 0 | days@ | 0 | /day | 0 |  | 0
| Equipment Sub-Total = |  |  |  | 0
SUPPLIES & DISBURSEMENTS
Field & Office supplies including disbursements |  | days@ | 0 | /day | 0
Accommodation | 0 | days@ | 0 | / 2 people/day | 0
Subsistence | 0 | days@ | 0 | / 2 people/day | 0
Mobilization/Demobilization |  | mob/demob@ | 0 | /mob/demob | 0
| Supplies & Disbursements Sub-Total = |  |  |  | 0
|  |  | TOTAL (Excluding GST) |  | 0
mob-demob | unit | rate | total
distance (one way) |  |  | 0
crew hourly charges (one way) |  | 0 | 0
Total (one way) |  |  | 0
| Total Mob/demob |  | 0
Estimated cost of pursuit | 0
Subcontractor Costs | 0
| gross revenue |  |  | 0
| sub contractors |  |  | 0
| expenses (equip, supplies, subsistence) |  |  | 0
| non - billable expenses (estimate) |  |  | 0
| net revenue |  |  | 0
| billable labour cost |  |  | 0
overhead
| net margin |  |  | 0
| Total Labour hours |  |  | 0
| Average rate Labour cost/hr |  |  | 0
| Direct Labour Cost |  |  | 0
| As Sold DLM |  |  | #DIV/0!
| Net Margin % |  |  | #DIV/0!

## project initiation summary
Project Team
name | role | responsibility | skills required and experience | expectations
| Project Director | ***linked to rate sheet
Project Manager
Project Coordinator
Geomatics Technician
Survey Crew
Survey Crew
Subconsultants / Subcontractors
name | company | expertise and responsibility | Contracted value | expectations
Expected Deliverables
| Description |  |  | Responsibility
Fieldwork
Officework
Communications Plan
| Format | Responsibility | Frequency
Internal
External

## resource request & instructions
Human Resource Request Form
A. Project Information
Project Number: |  |  | Project Name: |  |  | Client:
Project Manager: |  |  |  |  | Project Director:
Market Sector |  |  |  |  | Expected Start Date:
Type of work |  |  | Region |  | Expected End Date:
Date:
Project Scope:
Office Crew
Type of services required: |  | Geosptial Investigation | Desktop Analysis | Research | Data Analysis | Drawing / Plan Review | Drafting | Administration | QA / QC
Expected Level of Experience: |  |  |  | (junior/intermediate/senior)
Projected hours to complete works:
Office Instructions
Field Crew
Number of Crews Required: |  |  |  | Expected Level of Experience: |  |  | (junior/intermediate/senior)
Skills required by crew: |  | Line locating | Control Network establishment | Engineering Surveys | Construction Surveys | Hydrographic Surveys | High Precision Surveys | Cadastral Surveys | UAV Surveys
|  | Other Qualifications: |  |  |  |  | Shift Duration:
Field scope Instructions
Control | Control location | Datum |  | Field scope details
Survey data package
kml | dxf | ascii
Safety Training required |  |  |  |  | Special PPE
Other: |  |  |  |  | Other:
Special Equipment Required to complete the work |  |  |  |  | Field Supplies and Materials
Other: |  |  |  |  | Other:
Site Location
| Sec. | Twp. | Rge. | Meridian |  |  | Map - Google Earth
| longitude |  | latitude
UTM Coordinates
Client Management Instructions
Meeting is Required: |  | yes/no |  | >>> with |  |  | Other:
Meeting Location:
Meeting Date: |  |  | Time: |  | Contact Name:
Phone Number(s): |  |  |  | Crew to Contact Landowner: |  |  | Owner Info:
Accommodation
Hotel/Camp required?: |  |  |  | Nearest Center/camp:
Accomodation to be arranged by: | [7 empty] | Other:
Crew to Contact Landowner |  | Y
N
N/A
File Number:
Characters | 1
2
3
4
5
6
7
8
9
|  | *** |  | to be used as a selection tool
to be filled in by Project Manager

## hazard identification
Project Execution Hazard Identification and Control
| Specific Task | Type of hazard | Probability of hazard to occur | control | responsibility
Fieldwork
Officework
Project Risk Register
Risk | Risk Trigger | Risk Response | Risk Impact

## emergency response plan
PROJECT INFORMATION: |  |  |  |  | PROJECT LOCATION
Project number |  |  |  |  | Latitude | Dec. Deg.
CLIENT: |  |  |  |  | Longitude | Dec. Deg.
Project name: |  |  |  |  | Legal
GOOGLE EATH MAP AND DIRECTIONS TO SITE |  |  |  |  | JOURNEY MANAGEMENT PLAN
LINK TO GOOGLE EATH MAP AND DIRECTIONS TO SITE
PLANNED TRAVEL DATE:
FIELD CREW
NAME: |  |  | CELL |  | EMAIL:
NAME: |  |  | CELL |  | EMAIL:
CLIENT INFORMATION
PROJECT MANAGER
| NAME: |  | EMAIL |  | CELL:
SITE CONTACT |  |  | EMAIL
| NAME: |  | EMAIL |  | CELL:
INFORMATION
PROJECT DIRECTOR
|  |  | EMAIL |  | CELL:
PROJECT MANAGER
| NAME: |  | EMAIL |  | CELL:
PROJECT COORDINATOR
| NAME: |  | EMAIL |  | CELL:
CREW SUPERVISOR
| NAME: |  | EMAIL |  | CELL:
SAFETY SUPERVISOR
| NAME: |  | EMAIL |  | CELL:
NEAREST HEALTH CENTRE
| NAME: |  | ADDRESS
PHONE
EMERGENCY PHONE NUMBERS If in doubt, call 911.
R.C.M.P.: |  | PHONE: |  | POISON CENTRE: | PHONE:
AMBULANCE: |  | PHONE: |  | FIRE: | PHONE:
HOSPITAL: |  | PHONE:
24 hour reporting for fires in all areas
HEALTH LINK: |  | PHONE:

## crew deployment checklist
Project Name: |  |  | Project No.:
Work Location: |  |  | PO #:
Deployment |  | N/A | Reviewed/ |  | Notes
Discussed
Field Booklet |  | ☒ | ☐
Accommodation Location |  | ☒ | ☐
Field office location |  | ☒ | ☐
Field Supplies |  | ☐ | ☒
Office and Field point of contacts |  | ☒ | ☐
Client Office and Field point of contacts |  | ☐ | ☒
Mob-Demob charges |  | ☒ | ☐
Time charging |  | ☐ | ☒
Survey Permission Line List |  | ☒ | ☐
Scope of Work |  | N/A | Reviewed/ |  | Notes
Discussed
Scope of work clearly defined and communicated |  | ☐ | ☒
Review all pertinent information in project area (including data from other jobs in the area) |  | ☒ | ☐
Work breakdown structure (Timesheets) |  | ☐ | ☒
Hours of Work & Rotation Schedule |  | ☒ | ☐
Review of Drawings and Plans |  | ☐ | ☒
Review of DXF, SHP or KMZ files |  | ☒ | ☐
Coordinate System/Frequency |  | ☐ | ☒
Quality |  | N/A | Reviewed/Discussed |  | Notes
Project Quality Plan |  | ☐ | ☒
Previous project NCRs |  | ☒ | ☐
Applicable Lessons Learned |  | ☒ | ☐
Project checklists to be used |  | ☒ | ☐
QC checks to be done |  | ☒ | ☐
(e.g. Tool run checks, Odometer (distance) checks between AGMs and GWDs)
Received any applicable training for the project scope |  | ☒ | ☐
Applicable work instructions/workflows |  | ☒ | ☐
Safety |  | N/A | Reviewed/ |  | Notes
Discussed
JSA |  | ☐ | ☒
ERP |  | ☒ | ☐
Safety Tickets and Orientation |  | ☐ | ☒
Fatigue management |  | ☐ | ☒
Safety submission requirements |  | ☐ | ☒
FLRA DHA WSM ATV DVW SOC
Inspection requirements |  | ☒ | ☐
TRUCK ATV SLED ARGO BOAT TRAILER UTV
Journey Management Procedures |  | ☒ | ☐
Risks related to SOW |  | ☐ | ☒
Specific Check In/Check Out Procedures |  | ☐ | ☒
Specific PPE Required |  | ☐ | ☒
Wildlife Monitor Required? |  | ☒ | ☐
Equipment |  | N/A | Reviewed/ |  | Notes
Discussed
Project Specific Equipment (i.e. Total Station, Probe, Vivax, Fuji, Level, Satellite Phone, InReach) |  | ☒ | ☐
Equipment Calibrated? (i.e. Survey Equipment, Locating equipment) |  | ☒ | ☐
Additional requirements? |  | ☒ | ☐
Comments:
Title | Printed Name |  |  | Signature |  | Date
(yyyy-mm-dd)
Project Manager
Crew

## daily PM project journal
Weekly Data:
[11 empty] | #REF! | Site Occupancy Days (Brought Forward)
Weekly Progress Report Number |  |  |  | 0 | Enter: Last Week's Weekly Progress Number | [5 empty] | #REF! | Pre Scheduled 8 Days Off Cycle (Brought Forward)
(Last Week): | [10 empty] | #REF! | Inclement Weather Days (Brought Forward)
|  |  | Project Journal - Weekly report |  |  |  |  | Report # 1 |  |  | #REF! | Site Occupancy 30 Day Cycle (Last Week)
[10 empty] | This Week | Total to Date
Project: | [5 empty] | Location: |  |  | Site Occupancy | 0 | #REF!
Client | [5 empty] | Contract Number: |  |  | Pre Scheduled Day Off | 0 | #REF!
Week Ending: | 2020-07-18 |  |  |  |  | Project Manager: |  |  | Inclement Weather Day | 0 | #REF!
[9 empty] | Break Check | 0 |  | If Zero, Project is on Preschedule Phase Break or Winter Shutdown
DATE & DAY |  |  |  | DAILY PROGRESS AND COMMENTS |  |  |  |  | Site Occupancy Cycle Count |  | #REF! | Tracking of 30 Day Cycle
2020-07-12
Weather |  | Review of SCOPE: | Y/N | [5 empty] | Site Occupancy | 0 | #REF!
Temp: |  | Review of FLHA: | Y/N | [5 empty] | Pre Scheduled Day Off | 0 | #REF!
Pressure: |  | Crew Check-in | Y/N | [5 empty] | Inclement Weather Day | 0 | #REF!
Humidity: |  | Review of FIELD DATA | Y/N | [5 empty] | Break Check | 0
[9 empty] | Site Occupancy Cycle Count |  | #REF!
2020-07-13
Weather |  | Review of SCOPE: | Y/N | [5 empty] | Site Occupancy | 0 | #REF!
Temp: |  | Review of FLHA: | Y/N | [5 empty] | Pre Scheduled Day Off | 0 | #REF!
Pressure: |  | Crew Check-in | Y/N | [5 empty] | Inclement Weather Day | 0 | #REF!
Humidity: |  | Review of FIELD DATA | Y/N | [5 empty] | Break Check | 0
[9 empty] | Site Occupancy Cycle Count |  | #REF!
2020-07-14
Weather |  | Review of SCOPE: | Y/N | [5 empty] | Site Occupancy | 0 | #REF!
Temp: |  | Review of FLHA: | Y/N | [5 empty] | Pre Scheduled Day Off | 0 | #REF!
Pressure: |  | Crew Check-in | Y/N | [5 empty] | Inclement Weather Day | 0 | #REF!
Humidity: |  | Review of FIELD DATA | Y/N | [5 empty] | Break Check | 0
[9 empty] | Site Occupancy Cycle Count |  | #REF!
2020-07-15
Weather |  | Review of SCOPE: | Y/N | [5 empty] | Site Occupancy | 0 | #REF!
Temp: |  | Review of FLHA: | Y/N | [5 empty] | Pre Scheduled Day Off | 0 | #REF!
Pressure: |  | Crew Check-in | Y/N | [5 empty] | Inclement Weather Day | 0 | #REF!
Humidity: |  | Review of FIELD DATA | Y/N | [5 empty] | Break Check | 0
[9 empty] | Site Occupancy Cycle Count |  | #REF!
2020-07-16
Weather |  | Review of SCOPE: | Y/N | [5 empty] | Site Occupancy | 0 | #REF!
Temp: |  | Review of FLHA: | Y/N | [5 empty] | Pre Scheduled Day Off | 0 | #REF!
Pressure: |  | Crew Check-in | Y/N | [5 empty] | Inclement Weather Day | 0 | #REF!
Humidity: |  | Review of FIELD DATA | Y/N | [5 empty] | Break Check | 0
[9 empty] | Site Occupancy Cycle Count |  | #REF!
2020-07-17
Weather |  | Review of SCOPE: | Y/N | [5 empty] | Site Occupancy | 0 | #REF!
Temp: |  | Review of FLHA: | Y/N | [5 empty] | Pre Scheduled Day Off | 0 | #REF!
Pressure: |  | Crew Check-in | Y/N | [5 empty] | Inclement Weather Day | 0 | #REF!
Humidity: |  | Review of FIELD DATA | Y/N | [5 empty] | Break Check | 0
[9 empty] | Site Occupancy Cycle Count |  | #REF!
2020-07-18
Weather |  | Review of SCOPE: | Y/N
Temp: |  | Review of FLHA: | Y/N
Pressure: |  | Crew Check-in | Y/N
Humidity: |  | Review of FIELD DATA | Y/N
Additional Comments:
Project Manager's Signature: | [6 empty] | Client's Signature:

## Project lessons learnt
Project Lessons learnt Summary
1. Were the project goals attained?
2. What went well? Provide examples of successes that happened during or because of the project
3. What didn’t go well? Discuss unintended outcomes that happened during or because of the project
4. What might have been better handled if done differently?
5. What recommendations would you give to others who might be involved in future projects of a similar type?
6. What was beyond your control?
7. What things surprised you on the project that were not planned?
8. What things did you anticipate happening that did not happen?
9. What mistakes did you successfully avoid making?
10. What could we automate or simplify that we do repetitively?
11. What skills did you need that were missing on this project?